## Sheet1
HouseKeeping Risk Analysis
Risk: | Probabilty of Occuring: | Impact On Project: | Risk Classification: | Midigation Stratigies:
Gameplay Mechanics confuse players or are not fun. | Medium | Medium | 3 | Obtain feedback from prototype and iterate on mechanics that are considered "unfun".
The project looses team members due to unfortunate circumstances. | Low | High | 1 | Use instructors guidance to get help from other students in the class if we are having trouble. Students can take up other team roles to get the job done.
Team members disagree on aspects of the project. | High | Low | 4 | Have team members compromise on ideas they really want to have inside the project. Or even add both ideas to said project if capacity allows.
Unity crashes causing lost assets and time. | Medium | Medium | 3 | Use Plastic to provide critical backups on the whole project. Have team members save their checkout in Google drive on their own personal computers so they have a backup.
Team members or Producers computer fails or stops working properly. | Low | Medium | 2 | Have team members attempt to troubleshoot computer using ACC's IT team or themselves. If that fails they will contact Deanna to have her possibly provide a computer. Or provide a space that teammembers can work in at ACC.
Team members loose motivation or drive. | Medium | Medium | 3 | Provide team members with support and encouragement for them to keep going on. Ask professors for guidance if issues are serious enough.
One of the team members needs to miss a few days during the semester. | High | Low | 4 | Other team members can fill in if one needs to miss a few days. Or team members can take their laptops or find a laptop to use to bring with them elsewere to work.
Some of the team members are unsure of what to do. | High | Low | 4 | Team members will help eachother out weather its technical or something else. If a situation occures were team members cant help it can be brought up to Gaber
Weather effects Team members House Power. | Medium | High | 2 | Team members will work while they still have power. However once they loose power they can pick it back up once they get power. Team members are also able to use ACC Campuses when open for Wifi.
Team misses goals they want to get done for a Milestone. | High | Medium | 3 | If Team misses goals they want to get done for a milestone. We will take the loss and discuss in the next meeting after the milestone. Making those missed goals a top priority. Along with what we can get into the project in reasonable time.
Team is unable to make in-person playtest meetings. | Medium | Medium | 3 | If Team members are unable to make in-person playtests, during the spring specifically, then they can playtest at home. We can also get other members of the team to come test with us at Campus so we can still have 4 players playtesting. Summer Team will plan to meet in person at Highland in the classroom for meetings and work.